## Trail W46
Trial week 46 - TR 15
TRIAL | Cellulose | PVA mix | Formulation | Duration | Comments | Stamping simulation | Testing to decide next prototyping | Sequence |  | ITC | When? | # samples | Dimension | Naming | NBK | When? | # samples
623047 | Cellulose 2,4% | new PVA mix | PVA 1,5% A40/6mm + 1,0% A20/6mm | 2 stacks | Press Issue | 1 board | Cutting at 2 wks curing | 1 | Day 1 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Impact test | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Bending | 2w + Finished
623047 | Cutted | (Max 6 planks available) | Sampleing after 2 weeks depends on samples needed! | [6 empty] | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Density | 2w + Finished
[15 empty] | Bending | 2w + Finished
623046 | Cellulose 2,8% | new PVA mix | PVA 1,5% A40/6mm + 1,0% A20/6mm | 5h |  | 1 board | Cutting at 2 wks curing | 2 | Day 1 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Impact test | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Bending | 2w + Finished
623046 | Cutted | (Max 6 planks available) | Sampleing after 2 weeks depends on samples needed! | [6 empty] | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Density | 2w + Finished
[15 empty] | Bending | 2w + Finished
623046 | Cellulose 2,8% | new PVA mix | 8 layer run instead of 10 | 1 stack |  | 1 board | Cutting at 2 wks curing | 2 | Day 1 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Impact test | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Bending | 2w + Finished
619022 | Cellulose 2,8% | PVA standard 100% A40 | STD Production (619022) | 2h |  | 1 board | Cutting at 2 wks curing | 3 | Day 1 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Impact test | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Bending | 2w + Finished
[10 empty] | Heat rain movement | Finished
[10 empty] | Oven cyclic movement | Finished
[10 empty] | Freeze Thaw | Finished
[10 empty] | Ring Test | Finished
[10 empty] | Cobb Test | Finished
619022 | Cutted | (Max 6 planks available) | Sampleing after 2 weeks depends on samples needed! |  |  |  |  | 3 | Day 1 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Heat rain movement | Finished |  |  |  | Bending | 2w + Finished
[10 empty] | Oven cyclic movement | Finished
[10 empty] | Freeze Thaw | Finished
[10 empty] | Ring Test | Finished
[10 empty] | Cobb Test | Finished
623048 | Cellulose 2,8% | PVA standard 100% A40 | 15% limestone (reduce cement) | 2 stacks |  | 1 board | Cutting at 2 wks curing | 5 | Day 2 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Impact test | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Bending | 2w + Finished
[10 empty] | Heat rain movement | Finished
[10 empty] | Oven cyclic movement | Finished
[10 empty] | Freeze Thaw | Finished
[10 empty] | Ring Test | Finished
623048 | Cutted | (Max 6 planks available) | Sampleing after 2 weeks depends on samples needed! |  |  |  |  | 5 | Day 2 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Heat rain movement | Finished |  |  |  | Bending | 2w + Finished
[10 empty] | Oven cyclic movement | Finished
[10 empty] | Freeze Thaw | Finished
[10 empty] | Ring Test | Finished
623049 | Cellulose 2,8% | PVA standard 100% A40 | 15% limestone (reduce cement) - Half Mitsui 0,95% | 2 stacks |  | 1 board | Cutting at 2 wks curing | 6 | Day 2 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Heat rain movement | Finished |  |  |  | Bending | 2w + Finished
[10 empty] | Oven cyclic movement | Finished
[10 empty] | Freeze Thaw | Finished
[10 empty] | Ring Test | Finished
623049 | Cutted | (Max 6 planks available) | Sampleing after 2 weeks depends on samples needed! |  |  |  |  | 6 | Day 2 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Heat rain movement | Finished |  |  |  | Bending | 2w + Finished
[10 empty] | Oven cyclic movement | Finished
[10 empty] | Freeze Thaw | Finished
[10 empty] | Ring Test | Finished
623052 | Cellulose 2,8% | PVA standard 100% A40 | 15% limestone (reduce cement) - No Mitusi | 2 stacks |  | 1 board | Cutting at 2 wks curing | 7 | Day 2 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Heat rain movement | Finished |  |  |  | Bending | 2w + Finished
[10 empty] | Oven cyclic movement | Finished
[10 empty] | Freeze Thaw | Finished
[10 empty] | Ring Test | Finished
623052 | Cutted | (Max 6 planks available) | Sampleing after 2 weeks depends on samples needed! |  |  |  |  | 6 | Day 2 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Heat rain movement | Finished |  |  |  | Bending | 2w + Finished
[10 empty] | Oven cyclic movement | Finished
[10 empty] | Freeze Thaw | Finished
[10 empty] | Ring Test | Finished
523050 | Cellulose 2,8% | PVA standard 100% A40 | 25% limestone (reduce cement) | 2 stacks |  | 1 board | Cutting at 2 wks curing | 8 | Day 2 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Heat rain movement | Finished |  |  |  | Bending | 2w + Finished
[10 empty] | Oven cyclic movement | Finished
[10 empty] | Freeze Thaw | Finished
[10 empty] | Ring Test | Finished
523050 | Cutted | (Max 6 planks available) | Sampleing after 2 weeks depends on samples needed! |  |  |  |  | 6 | Day 2 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Heat rain movement | Finished |  |  |  | Bending | 2w + Finished
[10 empty] | Oven cyclic movement | Finished
[10 empty] | Freeze Thaw | Finished
[10 empty] | Ring Test | Finished
623051 | Cellulose 2,8% | PVA standard 100% A40 | Silam 3,5% + 0,45% Hydrophobation (Wacker) | 2 stacks |  | 1 board | Cutting at 2 wks curing | 9 | Day 2 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Impact test | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Bending | 2w + Finished
[10 empty] | Heat rain movement | Finished
[10 empty] | Oven cyclic movement | Finished
[10 empty] | Freeze Thaw | Finished
[10 empty] | Ring Test | Finished
[10 empty] | Cobb Test | Finished
623051 | Cutted | (Max 6 planks available) | Sampleing after 2 weeks depends on samples needed! |  |  |  |  | 9 | Day 2 | Point load | Finished |  |  |  | Delamination | 2w + Finished
[10 empty] | Hydric movement | Finished |  |  |  | Density | 2w + Finished
[10 empty] | Heat rain movement | Finished |  |  |  | Bending | 2w + Finished
[10 empty] | Oven cyclic movement | Finished
[10 empty] | Freeze Thaw | Finished
[10 empty] | Ring Test | Finished
[10 empty] | Cobb Test | Finished
Constant for all tests because "best practice": |  |  | Simulation stamping
°SR 50-55 |  |  | Cut planks of +/- 20 cm before pressing with rotating tool
max press curve |  |  | Measure thickness before / after pressing of non stamped and stamped boards
2 stack pressing
depiling temp.55°-60 |  |  | Testing
- Protocol for depiling / curing time
- Save color data at Kuper
- standard testing at NBK after xx weeks
|  |  | - testing at ITC: cut boards at 2 weeks curing | 12 pieces - width of a plank (17,5 cm) x 50 cm long
- standard board pressed without stamping
- material with stamping simulation
4 pieces for '3 point bending after 24 hours saturation
density by "geometry" and water saturation
Subsequent trials |  |  | Additional test trial 1 (ref) + 7 (hydrophob): | 3 point bending after 48 hours saturation
Preparation of suitable stamping frame
Soft body impact: only on promising formulations at ITC
Duration | Stamping | Formulation
8 hours | Yes/No | Formulation 1 | Pre-carbonatation
8 hours | Yes/No | Formulation 2 | ITC: precarbonate 14h holding time samples trial 1 / 6 / 7 pre stamped and not stamped
2 stacks | Yes/No | Further reduction Mitsui |  | Ring test + CO2 absorption
2 stacks | Yes/No | Further tuning of limestone | NBK: pre-carbonatation after 5 wks curing in industrial chamber
Test decks

## Road map
Action overview | Comments | How to accelerate? | Budget | Q3/23 |  |  | Q4/23 |  |  | Q1/24 |  |  | Q2/24 |  |  | Q3/24 |  |  | Q4/24 |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
Overview of workstreams |  |  |  | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Production weeks |  |  |  | Q4/23 11: 46; Q1/24 1: 3; Q1/24 2: 9; Q2/24 4: 17; Q2/24 6: 24; Q3/24 9: 36; Q4/24 10: 41; Q4/24 11: 45
Supply chain
Replacement of Vats | PM3 used for slates and terrace | bar: 2025 Q3
Evalution of maximum production capacity | With slates and equitone | bar: Q1/24 2; Q3/24 7; 2025 Q1; 2025 Q3; 2026 Q1; 2026 Q3; 2027 Q1; 2027 Q3; 2028 Q1; 2028 Q3
Decision on additional hatschek (Opp. / Feas. / Comm.) | Ambition plan? NBK / Somewhere else? |  |  | 2026 Q4: CIC; 2027 Q3: CIC; 2028 Q4: ->
Decision on new finishing line (Opp. / Feas. / Comm.) |  |  |  | Q1/24 3: Start eng.; Q4/24 12: CIC; 2025 Q3: CIC; 2027 Q3: X
Adjust automation on press | Current automation is difficult for trials
Delamination
Trials new fibers 4 stacks | Improved dewatering (A20/6mm) | bar: Q3/23 7
Testing in the lab (ITC) | Bending / Point load / Impact test | bar: Q3/23 8 to Q4/23 10
Recalculation for non residential use | Consult Julien Soulhat | bar: Q3/23 9
Redo fiber test for 8h for verification | Adjusted pressing + refining cellulose | bar: Q4/23 11
Quick testing after 2 weeks of curing | Sampleing, shipping W49, Testing W50/51 | Implementation of quick testing to preeveluate | bar: Q4/23 12
Finishing + Carbonation and testing of fibre test | Finished in W03 -> Shipping | bar: Q1/24 1
Full testing of Material | Finished in W06? | bar: Q1/24 1 to Q1/24 2
Verification of process on long tests | 50% material should be sellable, before 135.000€ | Do it without results from long term test (higher risk) | 270000 | bar: Q1/24 2
Evaluation of reduced cycle time | PCO impact? | bar: Q4/23 12
Long term testing in the lab (ITC), Freeze Thaw? | Redo first tests | bar: Q1/24 1 to Q1/24 3
Release of best practices from test | Adaption to STD production / PQ plan | bar: Q1/24 3
Remove stress test | According to release critera | bar: Q1/24 3
Shrinkage
Evaluation of tests kits outside expo | KOB / Rennes / Portillio | bar: Q3/23 7 to Q2/24 5
Additional kit desinged for shrinkage tests | Avignon installed 25/10 | bar: Q3/23 9 to Q2/24 5
Proceed with testing procedure ITC lab | Influence of reversable and irreversable portion of shinkage | bar: Q3/23 7 to Q4/23 12
Ideation of new shinkage tests (short term solution) | Fixing methods / technical guidelines / subconstruction | Possibilities? each heating test with shrinkage measurement takes for 3 weeks. In each test we can evaluate 4 samples ( = 2.56m), TZD 02/11/2023 | bar: Q3/23 7 to Q4/23 12
Assessment on shrinkage claims | Date / Weather / Financial impact -> Steven | bar: Q4/23 11 to Q4/23 12
First industrial trails | Hydrophobation in mass / reduction cement |  | 25000 | bar: Q4/23 11
Finishing + Carbonation and testing of fibre test | Finished in W03 -> Shipping | bar: Q1/24 1; Q1/24 3; Q2/24 6
Full testing of Material | Finished in W8 | More test benches for shrinkage testing needed? External? | bar: Q1/24 1 to Q1/24 2; Q2/24 4 to Q2/24 5; Q3/24 7 to Q3/24 8
Ideation of new shrinkage | Based on restults of testing | Quick testing possible? When first results? | bar: Q1/24 2 to Q1/24 3
Additional trails series based on results | Test procedure to be defined 6 smaller trails 4 big trails (2 productions lost to scrap) | Maybe testrun needed on preliminary results -> higher risk | 300000 | bar: Q1/24 3; Q2/24 6; Q3/24 9
Carbonation
Evaluation of inhouse testing | Installation conditions (weather/dust/vent) | bar: Q3/23 8 to Q3/23 9
Partial release of carbonation | bar: Q4/23 10 to Q4/23 11
Start production of material for pilot launch | TR05 / TR15 only carbonation | bar: Q1/24 1
Pilot launch | Decision on country + budget | bar: Q1/24 1 to Q3/24 9
Assessment of pilot launch | Claims / Feedback | bar: Q3/24 9
Process improvement on lab scale | R&D on pre-conditioning and cycle | bar: Q4/23 10 to Q3/24 9
Testing on industrial scale | 4 Tests (Formulation, Optimization of process control) |  | 32000 | bar: Q1/24 3; Q2/24 5; Q3/24 7; Q3/24 9
Prepare full launch + release | PQ plan in developedment by TFS | bar: Q3/24 9 to Q4/24 11
Full launch | bar: Q4/24 12
Additional humidifier | Fast ramp up | bar: 2025 Q1 to 2025 Q2
Additional racks to reach 100% capacity | Faster change over time | bar: 2025 Q1 to 2025 Q2
Installatiof automatic quality control | TBD
Decision additional chamber (Opp. / Feas. / Comm.) |  |  |  | 2025 Q1: CIC; 2025 Q4: CIC; 2026 Q2: X
PCO Optimisation
Incremental improvement while quality improvement | Carbonation/Delamination/Shrinkage | bar: Q3/23 7 to Q3/24 9
Mechanical testing of EterplanN mix | With new bar distance 315mm |  |  | Q4/23 11: Production; Q1/24 2: X
Trail with Eterplan adaptions | To pass failed tests |  | 8000 | bar: Q1/24 3 to Q2/24 5
Product development
Creation of 2nd gerneration Terrace (new mix?) | 20 trails on the mini hatschek + 20 trails extrusion |  | 400000 | bar: Q2/24 6 to Q4/24 12
Add brown color to the product pallet? | bar: Q1/24 1 to 2025 Q2
Re-evaluation of adding Semi-mass | bar: 2025 Q3
Development of adding Semi-mass | bar: 2025 Q3 to 2026 Q4
CEM2 Cement | not started
Recuperation of dust in the mix | not started
Replace Mitsui by recycled wood pulp | not started
Replace virgin by recycled cellulose | not started
Trading goods
Improving current offer | Screws / Clips | bar: Q3/23 7 to Q2/24 6
Additional supplier for trading goods | Depending on volumes | bar: 2025 Q2
Note on A12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Philippe Rubbrecht Timing adapted according to forecast from boost
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Julien Soulhat
Note on A28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: implement new PQ plan Reply: Was meant by the line 23. I will add it in the comments
Note on A30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On-going - first results presented
Note on A31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kit is installed 25/10/2023
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: only in Avignon Reply: KOB removed
Note on B32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: reversible and irreversible part
Note on A35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Philippe Rubbrecht Agreed test procedure integrated
Note on A39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ? do you mean trial productions for shrinkage mitigation if possible? Reply: Yes we included some small trails for verification of concept in the budget and some bigger trails for validation of the process… But the possibilities to remove the shrinkage are quite limited I think. Therefore the testing will be quite vague
Note on B47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: R&D on pre-conditioning and cycle
Note on B49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PQ plan tb developed
Note on B53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: part of PQ plan
Note on A68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: replace Mitsui by recycled wood pulp and replace virgin by recycled cellulose
Note on B68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: not started

## Test plan
Action overview | Comments | How to accelerate? | What ? | Who ? | Samples | Priority | Q3/23 |  |  | Q4/23 |  |  | Q1/24 |  |  | Q2/24 |  |  | Q3/24 |  |  | Q4/24 |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028
Overview of workstreams | [6 empty] | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Production weeks | [6 empty] | Q4/23 11: 46; Q1/24 1: 3; Q1/24 2: 9; Q2/24 4: 17; Q2/24 6: 24; Q3/24 9: 36; Q4/24 10: 41; Q4/24 11: 45
Supply chain
Replacement of Vats | PM3 used for slates and terrace | bar: 2025 Q3
Evalution of maximum production capacity | With slates and equitone | bar: Q1/24 2; Q3/24 7; 2025 Q1; 2025 Q3; 2026 Q1; 2026 Q3; 2027 Q1; 2027 Q3; 2028 Q1; 2028 Q3
Decision on additional hatschek (Opp. / Feas. / Comm.) | Ambition plan? NBK / Somewhere else? | [5 empty] | 2026 Q4: CIC; 2027 Q3: CIC; 2028 Q4: ->
Decision on new finishing line (Opp. / Feas. / Comm.) | [6 empty] | Q1/24 3: Start eng.; Q4/24 12: CIC; 2025 Q3: CIC; 2027 Q3: X
Adjust automation on press | Current automation is difficult for trials
Delamination
Trials new fibers 4 stacks | Improved dewatering (A20/6mm) | bar: Q3/23 7
Testing in the lab (ITC) | Bending / Point load / Impact test | bar: Q3/23 8 to Q4/23 10
Recalculation for non residential use | Consult Julien Soulhat | bar: Q3/23 9
Redo fiber test for 8h for verification | Adjusted pressing + refining cellulose | bar: Q4/23 11
Quick testing after 2 weeks of curing | Sampleing, shipping W49, Testing W50/51 | Implementation of quick testing to preeveluate | bar: Q4/23 12
Finishing + Carbonation and testing of fibre test | Finished in W03 -> Shipping | bar: Q1/24 1
Full testing of Material | Finished in W06? | bar: Q1/24 1 to Q1/24 2
Verification of process on long tests | 50% material should be sellable | Do it without results from long term test (higher risk) | 270000 | bar: Q1/24 2
Evaluation of reduced cycle time | PCO impact? | bar: Q4/23 12
Long term testing in the lab (ITC), Freeze Thaw? | Redo first tests | bar: Q1/24 1 to Q1/24 3
Release of best practices from test | Adaption to STD production / PQ plan | bar: Q1/24 3
Remove stress test | According to release critera | bar: Q1/24 3
Shrinkage
Evaluation of tests kits outside expo | KOB / Rennes / Portillio |  | - movement of full size plank - movement over butt joint | TZD | bar: Q3/23 7 to Q2/24 5
Additional kit designed for shrinkage tests outside expo | Avignon |  | - movement of the ends L+R full size - movement over butt joint | TZD | bar: Q3/23 9 to Q2/24 5
Proceed with testing procedure ITC lab | Influence of reversable and irreversable portion of shinkage | bar: Q3/23 7 to Q4/23 12
| repeat HR test with contineous displacement measurement |  | reversable/irreversable movement profile | TZD | ref non carbonated ref carbonated | P2 | bar: Q3/23 7 to Q4/23 12
Ideation of new shinkage tests (short term solution) | Fixing methods / technical guidelines / subconstruction - method 1 = fixed point middle using T clip 45°screw - method 2 = fixed point middle using stud - method 3 = fixed point middle using screw (see below) - method 4 = standard clips and stair-end overlaps | Normally each heating test with shrinkage measurement takes for 3 weeks. In each test we can evaluate 4 samples ( = 2.56m), TZD 02/11/2023 To accelerate we start from saturated condition and apply contineous 70°C surface heating for 1 week | movement at both ends L + R and compare differences | TZD | ref non carbonated TR05 | P1 | Q4/23 11: start W47 - end W50
| Fixing methods / technical guidelines / subconstruction - method 3 = one fixed point middle using screw | start from air dry condition and apply contineous 70°C surface heating for 1 week | movement at both ends L + R and compare differences as a reference test in parallel with standard clip fixing |  | ref non carbonated TR05 |  | Q4/23 11: method 3 started W45 - end W46
| Installation without 3mm space between planks = tight butt jointed |  | tb decided | bar: Q4/23 11
| connectors to camouflage the movement at the ends |  | 3D print, prototyping present to commercial team | bar: Q4/23 11
| testing of half length planks |  | tb decided | bar: Q4/23 11
| testing with two or more fixed points at supports in the middle area |  | tb decided | bar: Q4/23 11
impact of mixture trials W46 on shrinkage behavior | see test program in separate sheet | SAT 4 days and OD at 70¨C 3 days for 3 cycles 300 mm length |  |  | reference (PVA mix A20/A40) less cellulose 2,4% instead of 2,8% reduced SILAM & mass hydrophobation 15% and 25% of Limestone at expense of cement (reduced amounts of Mitsui) increased density by pre-cutting before pressing NON carbonated samples |  | Q1/24 1: starting W3 after 4-5 weeks curing
Assessment on shrinkage claims | Date / Weather / Financial impact -> Steven | bar: Q4/23 11 to Q4/23 12
First industrial trails | Hydrophobation in mass / reduction cement |  | 25000 | bar: Q4/23 11
Finishing + Carbonation and testing of fibre test | Finished in W03 -> Shipping | bar: Q1/24 1; Q1/24 3; Q2/24 6
Full testing of Material | Finished in W8 | More test benches for shrinkage testing needed? External? | bar: Q1/24 1 to Q1/24 2; Q2/24 4 to Q2/24 5; Q3/24 7 to Q3/24 8
Ideation of new shrinkage | Based on restults of testing | Quick testing possible? When first results? | bar: Q1/24 2 to Q1/24 3
Additional trails series based on results | Test procedure to be defined 6 smaller trails 4 big trails (2 productions lost to scrap) | Maybe testrun needed on preliminary results -> higher risk | 300000 | bar: Q1/24 3; Q2/24 6; Q3/24 9
Carbonation
Evaluation of inhouse testing | Installation conditions (weather/dust/vent) | bar: Q3/23 8 to Q3/23 9
Partial release of carbonation | bar: Q4/23 10 to Q4/23 11
Start production of material for pilot launch | TR05 / TR15 only carbonation | bar: Q1/24 1
Pilot launch | Decision on country + budget | bar: Q1/24 1 to Q3/24 9
Assessment of pilot launch | Claims / Feedback | bar: Q3/24 9
Process improvement on lab scale | R&D on pre-conditioning and cycle | bar: Q4/23 10 to Q3/24 9
Testing on industrial scale | 4 Tests (Formulation, Optimization of process control) |  | 32000 | bar: Q1/24 3; Q2/24 5; Q3/24 7; Q3/24 9
Prepare full launch + release | PQ plan in developedment by TFS | bar: Q3/24 9 to Q4/24 11
Full launch | bar: Q4/24 12
Additional humidifier | Fast ramp up | bar: 2025 Q1 to 2025 Q2
Additional racks to reach 100% capacity | Faster change over time | bar: 2025 Q1 to 2025 Q2
Installatiof automatic quality control | TBD
Investigate COBB test for carbonation quality control | feasibility |  | compare carbonated and non-carbonated
Decision additional chamber (Opp. / Feas. / Comm.) | [6 empty] | 2025 Q1: CIC; 2025 Q4: CIC; 2026 Q2: X
PCO Optimisation
Incremental improvement while quality improvement | Carbonation/Delamination/Shrinkage | bar: Q3/23 7 to Q3/24 9
Mechanical testing of EterplanN mix |  | only test critical parameters = point load and impact | point loading and soft body impact | EHA | trial production W48 Eterplan N mix NON carbonated |  | Q4/23 11: Production; Q1/24 2: X
Trail with Eterplan adaptions | To pass failed tests |  | 8000 | bar: Q1/24 3 to Q2/24 5
Product development
Creation of 2nd gerneration Terrace (new mix?) | 20 trails on the mini hatschek + 20 trails extrusion |  | 400000 | bar: Q2/24 6 to Q4/24 12
Add brown color to the product pallet? | bar: Q1/24 1 to 2025 Q2
Re-evaluation of adding Semi-mass | bar: 2025 Q3
Development of adding Semi-mass | bar: 2025 Q3 to 2026 Q4
CEM2 Cement | not started
Recuperation of dust in the mix | not started
Replace Mitsui by recycled wood pulp | not started
Replace virgin by recycled cellulose | not started
Trading goods
Improving current offer | Screws / Clips | bar: Q3/23 7 to Q2/24 6
Additional supplier for trading goods | Depending on volumes | bar: 2025 Q2
Note on A12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Philippe Rubbrecht Timing adapted according to forecast from boost
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Julien Soulhat
Note on A28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: implement new PQ plan Reply: Was meant by the line 23. I will add it in the comments
Note on A30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On-going - first results presented
Note on A31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Kit is installed 25/10/2023
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: only in Avignon Reply: KOB removed
Note on B32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: reversible and irreversible part
Note on A43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Philippe Rubbrecht Agreed test procedure integrated
Note on A47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ? do you mean trial productions for shrinkage mitigation if possible? Reply: Yes we included some small trails for verification of concept in the budget and some bigger trails for validation of the process… But the possibilities to remove the shrinkage are quite limited I think. Therefore the testing will be quite vague
Note on B55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: R&D on pre-conditioning and cycle
Note on B57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PQ plan tb developed
Note on B61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: part of PQ plan
Note on A77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: replace Mitsui by recycled wood pulp and replace virgin by recycled cellulose
Note on B77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: not started

## Sheet1
TRIAL | Cellulose | PVA mix | Formulation
623046 | Cellulose 2,8% | new PVA mix | PVA 1,5% A40/6mm + 1,0% A20/6mm
623047 | Cellulose 2,4% |  | PVA 1,5% A40/6mm + 1,0% A20/6mm
623048 | Cellulose 2,8% | PVA standard 100% A40 | 15% limestone (reduce cement)
623049 |  |  | 15% limestone (reduce cement) - Half Mitsui 0,95%
523050 |  |  | 25% limestone (reduce cement)
623051 |  |  | Silam 3,5% + 0,45% Hydrophobation (Wacker)
623052 |  |  | 15% limestone (reduce cement) - No Mitusi
619022 |  |  | STD Production (619022)